## Project Plan
|  |  | Topic 6 | [6 empty] | Topic 7 | [6 empty] | Independent Study | [6 empty] | Topic 8 | [6 empty] | Topic 9 | [6 empty] | Topic 10 | [6 empty] | Topic 11 | [6 empty] | Exam Revision
Days until mandatory completion | 44.4043 | time axis 2024-09-30 to 2024-11-22
Section | Repsonsibility | Status (Insert the codes as per the note) | time axis 2024-09-30 to 2024-11-22
Earned Value Management
Complete the EVM | All Members(Rohit Kumar Malik, Sajiya Narbandh, Muhammad Naseef) | GD | 2024-10-01: G; 2024-10-02: P; 2024-10-03: R
Quality Management Plan
2-Project Scope | Sajiya Narbandh | PD | 2024-10-03: G; 2024-10-10: P; 2024-10-23: R
3.1-Specific Roles in the organisation | Rohit Kumar Malik | PD | 2024-10-03: G; 2024-10-11: P; 2024-10-24: R
3.3-Team Organisation Diagram | Muhammad Naseef | G | 2024-10-04: G; 2024-10-12: P; 2024-10-25: R
3.3-Team Organisation and Lines of Responsibility explanation | Rohit Kumar Malik | G | 2024-10-04: G; 2024-10-12: P; 2024-10-25: R
4-Project Quality Standards | Sajiya Narbandh | G | 2024-10-09: G; 2024-10-20: P; 2024-10-31: R
5.1-Introduction to Project Testing | Muhammad Naseef | PD | 2024-10-07: G; 2024-10-15: P; 2024-10-28: R
5.2-Practical Implementation | Muhammad Naseef | G | 2024-10-08: G; 2024-10-16: P; 2024-10-29: R
Communications Plan
2-Project Scope | Rohit Kumar Malik | PD | 2024-10-03: G; 2024-10-14: P; 2024-10-26: R
3-Organisational Structure Diagram | Muhammad Naseef | PD | 2024-10-16: G; 2024-10-29: P; 2024-11-10: R
3-Organisational Structure Issues discussion | Rohit Kumar Malik | G | 2024-10-17: G; 2024-10-30: P; 2024-11-11: R
4.2-An explanation of the appoach | All Members(Rohit Kumar Malik, Sajiya Narbandh, Muhammad Naseef) | G | 2024-10-18: G; 2024-10-31: P; 2024-11-12: R
5.1-Formal Meetings | Rohit Kumar Malik | G | 2024-11-01: G; 2024-11-13: P; 2024-11-16: R
5.2-Formal Reports and Documents | Sajiya Narbandh | G | 2024-11-01: G; 2024-11-13: P; 2024-11-16: R
Appendix 1 - Matrix | All Members(Rohit Kumar Malik, Sajiya Narbandh, Muhammad Naseef) | G | 2024-10-18: G; 2024-10-31: P; 2024-11-12: R
Risk Management Plan
2-Project Scope | Muhammad Naseef | PD | 2024-10-03: G; 2024-10-14: P; 2024-10-26: R
5.1-Task 1 - Complete Appendix 1 - Risk Register | Sajiya Narbandh | G | 2024-10-30: G; 2024-11-06: P; 2024-11-13: R
5.2-Task 2 - Expected Monetary Value (EMV) | Rohit Kumar Malik | PD | 2024-11-01: G; 2024-11-08: P; 2024-11-15: R
Project Closure Review (PCR)
Risk Mitigation Strategies | Muhammad Naseef | G | 2024-11-12: G; 2024-11-13: P; 2024-11-14: R
Stakeholder Communication Plan | Rohit Kumar Malik | G | 2024-11-12: G; 2024-11-13: P; 2024-11-14: R
Timeline Adjustments and Resource Allocation | Sajiya Narbandh | G | 2024-11-12: G; 2024-11-13: P; 2024-11-14: R
Develop individual PCRs (These are not reviewed, but uploaded as is) | All Members(Rohit Kumar Malik, Sajiya Narbandh, Muhammad Naseef) | GD | bar: 2024-11-15 to 2024-11-17
Note on B3: MU: Insert the names or initials of the group member/s who will be responsibible for drafting this section of Assignment 2
Note on C3: ICT508: Use the following Status Codes: * GD - Green Review Drafting * G-Green Review Completed, * PD - Pink Review Drafting * P - Pink Review Completed * RD - Red Review Drafting (Finalise Draft for Red Review) * R-Red Review Completed - Ready for Submission
Note on A5: Initiate EVM development; ready for Green Review.
Note on A7: Drafting is in progress; needs completion before Green Review.
Note on A8: Finalize roles clearly for team efficiency.
Note on A9: Completed draft ready for review; ensure clarity in organization chart.
Note on A10: Ensure lines of responsibility are clear and aligned with organizational structure.
Note on A11: Ensure all quality standards are well documented and ready for review.
Note on A12: Drafting is ongoing; focus on introduction clarity.
Note on A13: Implementation strategy needs review to ensure practical application.
Note on A15: Finalize scope details; needs input from all members.
Note on A16: Create detailed diagram; ensure all roles are represented.
Note on A17: Identify issues to ensure smooth communication; ready for review.
Note on A18: Ensure all approaches are well-documented; ready for review.
Note on A19: Plan meeting structures; ensure schedule is clear.
Note on A20: Ensure reporting templates are ready for use.
Note on A21: Matrix must be detailed; ensure all matrices are aligned with project objectives.
Note on A23: Draft scope details; ensure alignment with overall risk management.
Note on A24: Risk register needs comprehensive details for assessment.
Note on A25: Drafting ongoing; focus on accurate calculations.
Note on A27: Strategies need to be actionable and realistic; ready for review.
Note on A28: Ensure communication plan addresses all stakeholders effectively.
Note on A29: Ensure resources are aligned with project timelines.
Note on A30: PCR drafts need to be prepared by all members for final review.